## I2.5 (hidden)
ELP | Summary | Responsible Dev | Development Progress | Pair testing (Pass or Not) | Responsible QA(Test Case) | Test case Progress | Testing Progress | Feedback By QA | Cross-Test QA | Cross Testing (Pass or Not) | Group Testing (Pass or Not) | Prepare Deployment | UAT | Remark
I 24
ELP-1029 | Instructor Notification: Send automated email notification to instructor when a learner interacts with one of their lessons
| Setting in "Lesson Option" | Jason Yuan | 90% | Pass | Wendy Zhong | 100% | 90% |  | Claire Du
| Send mail in admin site | Jason Yuan | 90% | Pass | Wendy Zhong | 100% | 90% |  | Claire Du
ELP-1035 | Improve text of message sent to instructor when learners write comments in lesson | Leo Gao | 90% | Pass | Claire Du | 100% | 100% |  | Kevin
ELP-1036 | "Changing Email Address" function in Admin site doesn't change the corresponding email address in mail server database (ExtMail) | Jason Yuan | 90% | Pass | Claire Du | 100% | 100% |  | Kevin
ELP-1024 | Group Topics: Option to prevent group members from attaching files or lessons to group topics | Markus Pang | [6 empty] | Xiaofan Yu
| Group Plocy setting | Leo Gao | 90% | Pass | Ruby Yu | 100% | 100% |  | Lucas Shi
| Modify authentication process of Post topic/Post comment/Edit Topic/Edit Comment | Leo Gao | 90% | Pass | Ruby Yu | 100% | 100% |  | Lucas Shi
| Group Plocy setting in admin site | Leo Gao | 90% | Pass | Ruby Yu | 100% | 100% |  | Lucas Shi
ELP-994 | Method for Group Owner to assign a GRADE to each lesson in the group (created in sub-account) | Markus Pang | [6 empty] | Xiaofan Yu
| Setting in "feature lesson" page | Leo Gao | 90% | Pass | Lucas Shi | 100% | 90% |  | Ruby
| Show up in feature lessons list | Leo Gao | 90% | Pass | Lucas Shi | 100% | 90% |  | Ruby
| Setting in "add lesson" function of topic and comments page | Jason Yuan | 90% | Pass | Lucas Shi | 100% | 90% |  | Ruby
| Showup in lesson list of topic/comment page | Jason Yuan | 90% | Pass | Lucas Shi | 100% | 90% |  | Ruby
ELP-1034 | Make "Search" by test name work as search function, not a filter function | Hunk Luan | 90% | Pass | Ruby Yu | 100% | 100% |  | Shaw
ELP-1024 | Group Topics: Option to prevent group members from attaching files or lessons to group topics | Jason Yuan | 90% | Pass | Xiaofan Yu | 100% | 90% |  | Lucas Shi
Enhancement
| Add "search" function for Enterprise group | Leo Gao | 90% | Pass | Lucas Shi | 100% | 90% |  | Ruby
| Hide "all lesson" of add lesson popup window. | Hunk Luan | 90% | Pass | Lucas Shi | 100% | 90% |  | Ruby
I 25
ELP - 1011 | Flow of Lesson Creation | Hunk Luan | 80% | Pass | Claire Du |  |  |  | Kevin Liu
| New payment process |  |  |  | Wendy Yue/Lucas |  |  |  | Yu
| Sign up and Creation Account | Sam Zhang | 90% | Not | Lucas Shi/Ruby Yu | 80% | 0% |  | Claire/Kevin
| Payment Process | Leo Gao | 90% | Not | Lucas Shi/Ruby Yu | 80% | 0% |  | Claire/Kevin
| Cronjob of payment check | Sam Zhang | 90% | Not | Lucas Shi/Ruby Yu | 80% | 0% |  | Claire/Kevin
| Email notification | Sam Zhang | 90% | Not | Lucas Shi/Ruby Yu | 80% | 0% |  | Claire/Kevin
| Brand Sign up | Sam Zhang | 50% | Not | Lucas Shi/Ruby Yu | 80% | 0% |  | Claire/Kevin
| Contributor White Label | Markus Pang | [6 empty] | Xiaofan Yu
| Flex part | Jason Yuan | 90% |  | Claire Du/Lucas Shi | 80% | 0% |  | Ruby/Kevin
| Marketing | Jason Yuan | 90% |  | Ruby Yu | 80% | 0% |  | Claire/Kevin
| Dashboard | Jason Yuan | 90% |  | Lucas Shi/Ruby Yu | 80% | 0% |  | Claire/Kevin
| Account Module |  |  |  | Wendy Yue/Lucas |  |  |  | Yu
| Group Themes | Hunk Luan | 90% |  | Ruby Yu | 80% | 0% |  | Claire
| Group Roles(Menu and Tabs) | Sam Zhang | 90% |  | Ruby Yu | 80% | 0% |  | Claire
| My Account Setting - Personal | Leo Gao | 90% |  | Kevin Liu/Lucas Shi | 80% | 0% |  | Claire/Ruby
| My Account Setting - My account | Sam Zhang | 90% |  | Kevin Liu/Lucas Shi | 80% | 0% |  | Claire/Ruby
| My Account Setting - Themes Setting | Hunk Luan | 90% |  | Kevin Liu/Lucas Shi | 80% | 0% |  | Claire/Ruby
| My Account Setting - My Activity | Leo Gao | 90% |  | Kevin Liu/Lucas Shi | 80% | 0% |  | Claire/Ruby
| Group Landing and Index (Dispatcher) | Sam Zhang | 85% |  | Ruby Yu | 80% | 0% |  | Kevin
| Group Invitation and joing process | Hunk Luan | 70% |  | Ruby Yu | 80% | 0% |  | Kevin
| Remove exiating features |  |  |  | Wendy Yue/Lucas |  |  |  | Yu
| Payment related functions | Jason Yuan | 55% |  | Lucas Shi | 80% | 0% |  | Claire/Ruby
| Category related functions | Leo Gao | 0% |  | Lucas Shi | 80% | 0% |  | Claire/Ruby
| Other removed functions | Leo Gao | 0% |  | Lucas Shi | 80% | 0% |  | Claire/Ruby
| Admin sit modifications |  |  |  | Wendy Yue/Lucas |  |  |  | Yu
User administration
| Bulk upload user(Remove group name) | Jason Yuan | 90% |  | Claire | 80% | 0% |  | Kevin
| Create new user form(Add group ID) | Jason Yuan | 90% |  | Claire | 80% | 0% |  | Kevin
| User List and User Profile | Jason Yuan | 90% |  | Claire | 80% | 0% |  | Kevin
| Group Administration (Group Admin/ Remove group name in upload CSV/ Remove enterprise) | Jason Yuan | 90% |  | Ruby Yu | 80% | 0% |  | Lucas Shi
| Suggested Lessons | Jason Yuan | 70% |  | Claire | 80% | 0% |  | Kevin
Group Modifications
| Group index page(remove feature groups/other groups/search groups) | Hunk Luan | 60% |  | Ruby Yu | 80% | 0% |  | Kevin/Lucas
| Group Description(Remove theme setting)(change validation of group name and URL) | Hunk Luan | 20% |  | Ruby Yu | 80% | 0% |  | Kevin/Lucas
| Group Policy(Remove hide function) | Leo Gao | 90% |  | Ruby Yu | 80% | 0% |  | Kevin/Lucas
| Group Member List | Hunk Luan | 40% |  | Ruby Yu | 80% | 0% |  | Kevin/Lucas
| Lesson/Course Management | Hunk Luan | 0% |  | Ruby Yu | 80% | 0% |  | Kevin/Lucas
| ELP-1053 Converting video to 480 kb/s bitrate | Jason Yuan | 90% |  | Lucas | 0% | 0% |  | Kevin
| ELP-991 Add account logo in all emails | Leo Gao | 0% |  | Lucas Shi/Ruby Yu/Kevin/Claire | 10% | 0% |  | Lucas Shi/Ruby Yu/Kevin/Claire
| All Test function | N.A | N.A | N.A | Shaw | 80% | 50% |  | Shaw
Admin site--QTP Team
| set up QTP enviroment | Markus Pang | 80% |  | QA | 70% | 50% |  | QA
| Re-code the QTP script | Markus Pang/Zou Lili | 70% |  | Lucas | N.A | 50% |  | N.A
| Make the testing datas | Markus Pang/Zou Lili & QA | 50% |  | QA | N.A | 50% |  | Lucas
| Testing | QA | 0% |  | Lucas | N.A | 0% |  | N.A

## 结对测试评审 (hidden)
Responsible QA | Responsible Dev | Feature Summary Of I 2.6 | Complexity status | Smoke/Pair Testing是否执行 | 测试用例覆盖度 | TC执行程度 | 是否测试了平台兼容性 | 互评：是否节省时间，提高效率 | Feedback By QA
Cao Hua | Bo Tao | Search and owner homepage
| Bo Tao | Dashboard
Claire Du | Hunk Luan | View Lesson Duration-Streaming hours
| Hunk Luan | Popup hints-setting
| Hunk Luan | Popup hints-Popup window
| Hunk Luan | UCSD Master report
| Hunk Luan | My lessons in Group
Lucas & Claire | Jason Yuan | Payment process--Test/Survey
| Jason Yuan | Multiple Accounts-Lesson/course:separated LO/tests:share
| Jason Yuan | Multiple Accounts-Mailing List
| Jason Yuan | Simply Lesson Options
| Jason Yuan | button for back group
Kevin Liu | Leo Gao | Payment process---Change Service Plan
| Leo Gao | Payment process-Toolbar setting and control
| Leo Gao | Payment process--Report/History
| Leo Gao | Account Payment-Back End (Knoodle Administration)
| Leo Gao | Backend email template
Ruby Yu | Sam Zhang | View Lesson Duration-Log analysis (crongjob)
Ruby Yu | Sam Zhang | Multiple Accounts-Invite and join, Account list
Claire Du | Sam Zhang | Multiple Accounts-Lesson permission(ClassroomController)
Ruby Yu | Sam Zhang | Display the number (and status) of people invited to join group
Ruby Yu | Sam Zhang | Change User Role in Group member tab
| Jim Bi | The toolbar that appears at bottom of virtual classroom partially covers the Powered by Knoodle footer - when page is fully scrolled down-new
| Jim Bi | Apply Beta Branding to Knoodle application - Utilize updated graphic logo
Boeing theme
黄色---Unknow feature 或不做的feature

## 手机端 - Main App
手机端 - Main App |  |  |  |  | 第一轮 |  | 第二轮 |  | 第三轮 |  | 第四轮 |  | 第五轮
测试环境（iPhone4, iPhone5, Android Samsung, Android 小米，Andoird 联想） |  |  |  |  | iPhone4 |  | iPhone5 |  | Android | 三星 | Android | 小米 | Android | 联想
功能模块 | 子模块 | # | 步骤 | 期望输出 | 实际输出 | 测试结果 | 实际输出 | 测试结果 | 实际结果 | 测试结果 | 实际结果 | 测试结果 | 实际结果 | 测试结果
应用页面Tab | 已安装应用 | 1.1 | 启动应用 | 显示已下载好OO代驾、OO拼车应用图标
|  | 1.2 | 检查无法访问服务器时的提示 | 提示“网络不通畅，请检查网络”
|  | 1.3 | 检查已安装应用显示 | 已安装应用框里边显示手机已安装的应用
|  | 1.4 | 检查未安装应用显示 | 未安装应用框里边显示手机未安装的应用
|  | 1.5 | user点击已安装的子App | 启动相应的App
|  | 1.6 | 点击未安装的子APP | 还没开始下载时: 提示“是否开始下载”，用户确认后开始下载对应APP，应用图标变为“正在下载”状态
|  | 1.7 |  | 正在下载时: 暂停下载，应用图标变为“暂停下载”状态
|  | 1.8 |  | 下载完未安装时:继续安装
|  | 1.9 | 一个未安装App正在下载时，点击另一个未安装App | 正在下载的App继续下载，新点击的App状态变为“暂停”状态
|  | 1.10 | 正在下载App时，退出App，从新启动App | 保存下载状态，重启后从最后状态继续下载。不要从头开始下载。
|  | 1.11 | 在后台更新子App的版本 | 相应的子App图标上边显示更新版本标识
|  | 1.12 | 点击已安装有升级标识的子APP | 提示“发现新版本X.X.X，是否升级”，用户确认后开始下载对应升级程序，用户取消则正常启动子APP
|  | 1.13 | 安卓用户按下返回键 | 非模态提示用户“再按一次退出OO车生活”，3秒内再次按下，退出应用
|  | 1.14 | 用户未登录，页面Tab切换到个人中心或通知中心 | 跳转到登陆页面
|  | 1.15 | 未读通知或公告查看 | 如有则在通知中心Tab按钮处显示未读标记，标记上数字显示未读条数
|  | 1.16 | 已下载完成后弹出模态提示 | 提示“是否安装”，选是进入安装，选否返回主屏，下载完成未安装的APP图标用特殊标记标出
|  | 1.17 | 同时点击多个待升级的App | 按时间先后顺序排列，完成或暂停前一个自动开始下一个
|  | 1.18 | 软件的正常启动 | 如果APP版本号第1段位更新，则必须升级才能启动
|  | 1.19 | 通知公告的检查条件 | 用户未登陆不检查通知公告
登录和注册 | 游客访问用户相关功能 | 2.1 | 游客访问消息中心、个人中心、分享标签 | 跳到登陆页面
| 登陆页面 | 2.2 | 检查登录部分显示是否正常 | 1.用户名输入框
|  | 2.3 |  | 2.密码输入框
|  | 2.4 |  | 3.自动登录复选框
|  | 2.5 |  | 4.忘记密码复选框
|  | 2.6 |  | 5.“登录”按钮
|  | 2.7 |  | 6.“注册”按钮
|  | 2.8 |  | 7.“忘记密码”链接
|  | 2.9 | 检查输入框默认显示 | 用户名输入框默认显示请输入用户名
|  | 2.10 |  | 密码输入框默认显示请输入密码
|  | 2.11 | user不输入用户名点击登录 | 提示信息：请输入用户名
|  | 2.12 | user输入用户名不输入密码点击登录 | 提示信息:请输入密码
|  | 2.13 | user输入错误的用户名密码，点击登录 | 提示信息：用户名或密码错误，请重试
|  | 2.14 | user输入正确的用户名错误的密码，点击登录 | 提示信息：用户名或密码错误，请重试
|  |  | user输入正确的密码错误的用户名，点击登录 | 提示信息：用户名不存在
|  |  | 用户勾选自动登录 | 软件自动勾选记住密码
|  |  | 用户取消勾选记住密码 | 软件自动取消勾选自动登录
|  |  | 用户名或密码有空格时 | 要求可以正常登录
|  |  | 首次登录“自动登录”和“记住密码”复选框状态 | 默认要求勾选
|  | 2.15 | user输入正确的用户名正确的密码，点击登录 | 进入消息中心页面Tab
|  | 2.16 | 选中“自动登录”正常登录，退出应用，从新启动 点击“消息中心”或“个人中心” | 不经过登录页面，自动登录
|  | 2.17 | 不选中“自动登录”正常登录，退出应用，从新启动 | 出现登录页面，不自动登录
|  | 2.18 | 选中“记住密码”，不选中“自动登录”正常登录，退出应用，从新启动 点击“消息中心”或“个人中心” | 自动显示最后登录成功的用户名和密码
|  | 2.19 | 不选中“自动登录”正常登录，退出应用，从新启动 | 不显示任何以前的用户名和密码
|  | 2.20 | 点击“注册”按钮 | 跳到注册页面
|  | 2.21 | 点击“忘记密码”链接 | 跳到忘记密码页面
|  | 2.22 | 点击左上角的返回按钮 | 跳到应用页面
| 忘记密码 | 2.23 | 检查部分显示是否正常 | 1. ”用户名“输入框
|  | 2.24 |  | 2. ”手机号“输入框
|  | 2.25 |  | 3. "获取验证码"按钮
|  | 2.26 |  | 4. ”验证码“输入框和验证码准确标识
|  | 2.27 |  | 5. ”输入新密码”输入框
|  | 2.28 |  | 6. “再次输入新密码”输入框
|  | 2.29 |  | 7. “确定"按钮
|  | 2.30 |  | 8. ”取消“按钮
|  | 2.31 | ”用户名“输入框为空，点击”获取验证码"按钮 | 提示“请输入用户名”
|  | 2.32 | 点击“手机号”输入框 | 出来Number Pad编辑器，不要出来综合编辑器
|  | 2.33 | 点击“验证码”输入框 | 出来Number Pad编辑器，不要出来综合编辑器
|  | 2.34 | ”手机号“输入框为空，点击”获取验证码"按钮 | 提示“请输入手机号”
|  | 2.35 | 输入不存在的用户名，点击“获取验证码” | 提示“您输入的用户名不存在”
|  | 2.36 | 输入用户名和手机号不匹配，点击“获取验证码” | 提示“您输入的手机号不正确”
|  | 2.37 | 输入非11位手机号，点击“获取验证码” | 提示“请输入有效的手机号”
|  | 2.38 | 输入正确的用户名和手机号，点击“获取验证码” | 接收到验证码短信
|  | 2.39 | 输入正确的验证码 | 验证码准确标识状态变为绿色
|  | 2.40 | 输入不正确的验证码 | 验证码准确标识状态变为灰色
|  | 2.41 | 输入6位以下的新密码，点击“确定” | 提示“密码长度至少6位”
|  | 2.42 | 密码两次输入不一致， 点击“确定” | 提示“密码输入不一致”
|  | 2.43 | 输入不正确的验证码，点击“确定” | 提示“验证码错误”
|  | 2.44 | 输入准确的验证码和一致的新密码，点击“确定” | 在服务器里更改用户密码，提示“您的密码已经重置，请牢记！”， 返回至“登录”页面
|  | 2.45 | 点击“取消” | 返回至“登录”页面
|  |  | 用户名和手机号不匹 | 提示“您输入的手机号不正确”
|  |  | 用户名的填写要求 | 仅支持英文大小写和数字，且以英文开头，长度为2-20
|  |  | 用户名未填写点击确定 | 提示“请输入用户名”
|  |  | 手机号未填写点击确定 | 提示“请填写手机号”
|  |  | 手机号填写字母或特殊字符 | 提示“请输入有效的手机号”或不允许输入
|  |  | 验证码和手机号不匹配 | 提示“请勿修改提交验证的手机号”
|  |  | 验证码未填写或不正确 | 提示“请填写正确的验证码”
|  |  | 验证码格试要求 | 验证码要求为4位纯数字
|  |  | 安卓手机点击获取验证码 | 验证码自动填写在验证码输入框
|  |  | 点击“获取验证码”按钮 | “获取验证码”为不可用状态，并进行1分钟倒计时，倒计时结束后按钮变为“重新获取”
|  |  | 验证码有效期 | 验证码有效期为5分钟，超时提交请求反馈“验证码已过期，请重新获取“
|  |  | 同一手机号多次获取验证码 | 最后一次获取的验证码有效
|  |  | 验证码和手机号不匹配 | 提示“请勿修改提交验证的手机号”
|  |  | “输入新密码”或“再次输入新密码” | 提示“请填写密码”
|  |  | “输入新密码”或“再次输入新密码”长度确认 | 密码长度范围为6-16，支持字母、数字、下划线，大小写敏感
|  |  | 重置密码成功 | 返回前一页面
|  |  | 重置密码失败 | 停留在忘记密码页面
| 用户注册 | 2.46 | 检查部分显示是否正常 | 1. “用户名”输入框
|  | 2.47 |  | 2. “手机号”输入框
|  | 2.48 |  | 3. “获取验证码”按钮
|  | 2.49 |  | 4. “验证码”输入框和验证码准确标识
|  | 2.50 |  | 5. “称呼”输入框
|  | 2.51 |  | 6. “先生”和”女士“选项框
|  | 2.52 |  | 7. ”密码“输入框
|  | 2.53 |  | 8. ”再次输入“输入框
|  | 2.54 |  | 9. ”邀请码“输入框，默认内容为”（可选）“
|  | 2.55 | ”用户名“输入框为空，点击”获取验证码"按钮 | 提示“请输入用户名”
|  | 2.56 | ”手机号“输入框为空，点击”获取验证码"按钮 | 提示“请输入手机号”
|  | 2.57 | 输入非11位手机号，点击“获取验证码” | 提示“请输入有效的手机号”
|  | 2.58 | 点击“手机号”输入框 | 出来Number Pad编辑器，不要出来综合编辑器
|  | 2.59 | 点击“验证码”输入框 | 出来Number Pad编辑器，不要出来综合编辑器
|  | 2.60 | 输入正确的用户名和手机号，点击“获取验证码” | 接收到验证码短信
|  | 2.61 | 输入正确的验证码 | 验证码准确标识状态变为绿色
|  | 2.62 | 输入不正确的验证码 | 验证码准确标识状态变为灰色
|  |  | 用户名的填写要求 | 仅支持英文大小写和数字，且以英文开头，长度为2-20
|  |  | 用户名已被占用时点击注册 | 提示“用户名太抢手，换一个试试？”
|  |  | 用户名未填写点击注册 | 提示“请输入用户名”
|  |  | 手机号未填写点击注册 | 提示“请填写手机号”
|  |  | 手机号填写字母或特殊字符 | 提示“请输入有效的手机号”或不允许输入
|  |  | 手机号码已经被注册过 | 提示“超时提交请求反馈“验证码已过期，请重新获取”
|  |  | 验证码和手机号不匹配 | 提示“请勿修改提交验证的手机号”
|  |  | 验证码未填写或不正确 | 提示“请填写正确的验证码”
|  |  | 验证码格试要求 | 验证码要求为4位纯数字
|  |  | 安卓手机点击获取验证码 | 验证码自动填写在验证码输入框
|  |  | 点击“获取验证码”按钮 | “获取验证码”为不可用状态，并进行1分钟倒计时，倒计时结束后按钮变为“重新获取”
|  |  | 验证码有效期 | 验证码有效期为5分钟，超时提交请求反馈“验证码已过期，请重新获取“
|  |  | 同一手机号多次获取验证码 | 最后一次获取的验证码有效
|  |  | 称呼未填写点击注册 | 提示“请填写称呼”
|  |  | 称呼默认勾选复选框 | 默认勾选“先生”
|  |  | 称呼填写要求 | 最多支持10个汉字，长度为2-20，支持汉字、字母、数字
|  |  | 密码未填写点击注册 | 提示“请填写密码”
|  |  | 密码长度过短 | 提示“密码长度至少6位”
|  |  | 密码长度确认 | 密码长度范围为6-16，支持字母、数字、下划线，大小写敏感
|  |  | “再次输入”未填写点击注册 | 提示“密码输入不一致”
|  |  | “密码”与“再次输入”的密码不一致 | 提示“密码输入不一致”
|  |  | “再次输入”长度确认 | 密码长度范围为6-16，支持字母、数字、下划线，大小写敏感
|  |  | 邀请码默认提示 | 提示“可选”
|  |  | 邀请码未非必输项 | 未输入邀请码要求可以正常注册
|  |  | 邀请码格试要求 | 6-8位字母加数字组合，大小写不敏感
|  |  | 注册成功后 | 跳转到进入登录界面之前点选的功能页面，并自动保存用户名密码，设定为自动登录
|  |  | 注册失败后 | 页面停留在注册页面
|  |  | 点击取消按钮 | 返回至“登录”页面
|  |  | 输入邀请码注册后，会给注册用户设置邀请码，并将邀请人的分成信息保存在注册用户账户中。 同时根据邀请码设置和注册城市点券自动发放策略，发放对应的点券给用户 | 此处需在对整个系统运作（特别是邀请码和点券的运作方式）充分了解的前提下，构造相应的测试用例
Note on E5: 作者: 具体设置路径是否要提示
Note on E37: 作者: 提示“密码输入错误”